## Sheet1
DEFECT TRACKING DOCUMENT
Defect No. | Date Created | Created By | Defect Description | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated time to fix in hours | Status | Resolution | Resolution date | Actual time to fix | Root Cause
1 | 2022-04-21 | Tester | User Not able to register | Development | High | Developer | 2022-04-14 | 2 | completed | corrected table name | 2022-04-14 | 1 hr | Missing correct table name
2 | 2022-04-21 | Tester | Searched movie was not showing in the table | Development | Medium | Developer | 2022-04-21 | 1 | Completed | corrected button | 2022-04-21 | 20 mins | missing button name
3 | 2022-04-21 | Tester | User not getting Unique ticket numbers | Development | High | Developer | 2022-04-21 | 2 | Completed | Eliminated duplicate numbers | 2022-04-21 | 1 hr | Generation of same number again and again